## Mappe 1
FESCA Project
| KW 25 | [6 empty] | KW 26 | [6 empty] | KW 27 (June-July) | [6 empty] | KW 28 | [6 empty] | KW 29 | [6 empty] | KW 30 | [6 empty] | KW 31 (July-August) | [6 empty] | KW 32 | [6 empty] | KW 33 | [6 empty] | KW 34 | [6 empty] | KW 35 | [6 empty] | KW 36 (September) | [6 empty] | KW 37 | [6 empty] | KW 38 | [6 empty] | KW 39 | [6 empty] | KW 40
| 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Unavailability of supervisors
Long | bar: F to F; M to F; M to F; M to F
Shaza | bar: M to F; M to F; M to F; M to F; M to F
Application Layer (Darya)
1a SQL Parsing (Query-AST) | bar: M to W
1b Logical Plan construction | bar: W to F
1c Physical Plan generation | bar: M to F; M to F; M to W
1d physical plan <-> MPC circuit translation, attention to and and xor | bar: M to F; M to F; M to F; M to F; M to F
Receive results from nodes, Reconstruct computation results | bar: M to F
3a Interface for Uploading tables (maybe application layer?)
3b Row Reader & Bit String Encoder
setup docker configuration file for all entities (Mimoun)
Crypto Layer
Generate correlated randomness (Alisher, Denis)
XOR gate execution (Alisher, Denis)
AND gate execution (implies gRPC) (Alisher, Denis) | bar: T
Composition execution (layer by layer)
3c Generating shares for tuple (implies generating randomness)
3d Generating shares of a table
Apply vectorizing (?)
Communication Layer
(from 1d) gRPC submit query as a circuit, maybe add. Info to all nodes, returns ack | bar: M to F; M to F
gRPC send result to analyst after computation
gRPC communication for MPC primitives | bar: T to W; T
gRPC send shares of tables to comp. nodes
Dockerize all entities / evaluation / wrapping up
Unit tests
Latency test: Small dataset
Latency test: Large dataset
Entities:
Data Owner (Mimoun)
Data Analyst (Darya)
Computing nodes
Dockerize all entities / evaluation / wrapping up