## Mappe 1
FESCA Project
| KW 24 | [6 empty] | KW 25 | [6 empty] | KW 26 | [6 empty] | KW 27 (June-July) | [6 empty] | KW 28 | [6 empty] | KW 29 | [6 empty] | KW 30 | [6 empty] | KW 31 (July-August) | [6 empty] | KW 32 | [6 empty] | KW 33 | [6 empty] | KW 34 | [6 empty] | KW 35 | [6 empty] | KW 36 (September) | [6 empty] | KW 37 | [6 empty] | KW 38 | [6 empty] | KW 39 | [6 empty] | KW 40
| 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Unavailability of supervisors
Long | bar: F to F; M to F; M to F; M to F
Shaza | bar: M to F; M to F; M to F; M to F; M to F
1 SQL Query Engine (Darya)
1a SQL Parsing | bar: M to W
1b Logical Plan construction | bar: W to F
1c Secrecy aligned MPC-aware cost model | bar: M to F; M to F; M to F; T to W; T
1d Query optimization | bar: W to F; M to F; T to W; T
1e Physical Plan generation | bar: M to F; M to F
1f Integration and testing | bar: M to F; M to F; M to F; M to F; M to F
2 MPC Runtime and oblivious operators
Setup Basics | bar: M to W
Data Splitting / Secret Sharing | bar: W to F; M to F; M
Database Operations | bar: M to F; M to F
Optimazations speed | bar: M to F
Cloud Deployment | bar: M to F; M to T
Final Checks | bar: T to F; M to F
3 Secret Sharing and data ingestion (Mimoun)
3a Interface for Uploading tables | bar: M to W
3b Row Reader & Bit String Encoder | bar: S to S
3c Generating shares for tuple | bar: T to S
3d Generating shares of a table | bar: M to F
3e Setting up the receive procedure | bar: M to F
3f Integration | bar: M to F
3g testing | bar: M to F
4 MPC Protocol layer